## Trang tính1
THE APPLICATION DEVELOPMENT PROJECT TOPIC (SWP391)
CLOTH SHOPPING SYSTEM ProductBacklog
Project: Online Shop |  | Total LOC:
# | Function/Screen | Feature | Level* | Function/Screen Details | Iteration | Deadline | In Charge | Status | In Time
1 | Home Page | Public | Simple | It allow everyone can view and search product in website | Iteration 1 | 2021-09-25 |  | Not Start | 2 Week
2 | Products List | Public | Simple | List of all the products for visitor to browsing | Iteration 1 | 2021-09-26 |  | Not Start
3 | Product Details | Public | Medium | Details like description, color, size, ... for customer to choose | Iteration 1 | 2021-09-27 |  | Not Start
4 | Cart Details | Customer | Complex | List of all the products that have been added into the card | Iteration 1 | 2021-09-28 |  | Not Start
5 | User Login | Common | Simple | User will login with account | Iteration 1 | 2021-09-29 |  | Not Start
6 | User Register | Common | Simple | Customer can register a new account here | Iteration 1 | 2021-09-30 |  | Not Start
7 | User Authorization | Common | Medium | Specifying access rights/privileges to resources or function | Iteration 1 | 2021-10-01 |  | Not Start
8 | Admin Dashboard | Admin | Complex | Statistic about new account, old account | Iteration 1 | 2021-10-02 |  | Not Start
9 | User Details | Admin | Medium | User can view information about account and update information | Iteration 1 | 2021-10-03 |  | Not Start
10 | Reset Password | User | Simple | User can retrieve password when forgotten by confirming information via email | Iteration 1 | 2021-10-04 |  | Not Start
11 | Change Password | User | Simple | It allow user can change new password | literation 2 |  |  | Not Start
12 | User List | Admin | Medium | Admin manage accounts | literation 2 |  |  | Not Start
13 | Cart Completion (Place Order) | Customer | Medium | Customer can comfirm order information like shipping information,... or change it | literation 2 |  |  | Not Start | 3 Week
14 | User Profile | User | Medium | User can view and update user's infomation | literation 2 |  |  | Not Start
15 | My Orders (xem lịch sử order) (Tổng quát) | Customer | Medium | Customers can view history of orders | literation 2 |  |  | Not Start
16 | Order Details (chi tiết) | Customer | Medium | Seller views the detail of 1 of his orders | literation 2 |  |  | Not Start
17 | Products List | Marketing | Medium | seller views and manages all products | literation 2 |  |  | Not Start
18 | Product Details | Marketing | Medium | Show information of product | literation 2 |  |  | Not Start
19 | Customers List | Marketing | Medium | Show list of all customer | literation 2 |  |  | Not Start
20 | Customer Details | Marketing | Medium | Show information of customer | literation 2 |  |  | Not Start
21 | Sale Dashboard | Marketing | Complex | Seller views Statistic of the sale of his products | literation 2 |  |  | Not Start
22 | Orders List For All Customer | Sales | Medium | Seller views list of all of orders | literation 2 |  |  | Not Start
23 | Order Details For Seller | Sales | Medium | The seller can see the orders, they can approve the order or not | literation 2 |  |  | Not Start
24 | Feedback | Public | Medium | User can view feedback from other customer about a product | literation 2 |  |  | Not Start
25 | Blogs List | Public | Medium | List of all the blogs for visitor to read | literation 3 |  |  | Not Start
26 | Blog Details | Public | Medium | Content of a blog | literation 3 |  |  | Not Start
27 | Notification | User | Medium | Show news about your order, replies,... | literation 3 |  |  | Not Start
28 | Error | Common | Simple | Placeholder when error occur | literation 3 |  |  | Not Start