## Cover
PROJECT REPORT
GROUP 1
This is a work status report for the week, and identifies plans and goals for the following weeks.
The report is summarized at the end of each week and will be updated in the future.
Members:
+ Trần Văn Đức (Leader- ductvhe141699);
+ Ngô Thị Ngọc Mai (maintnhe151402);
+ Nguyễn Duy Mạnh (MANHNDHE141170);
+ Bạch Ngọc Minh Châu(CHAUBNMHE153019);
+ Nguyễn Gia Phú (PHUNGHE150108);
+ Đinh Tiến Lâm(lamdthe153097).

## Week 4
Time: | 20/09/2021 - 24/09/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Database | Completed | Ready for the project
2 | Created working environment in Github for group | Completed | Completed in slot 8 (Monday, September 20, 2021)
3 | Learn how to connect Github and NetBean 8.2 | Completed | Completed in slot 8 (Monday, September 20, 2021) based on the video I sent in the chat box
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Complete the Data Dictionary section | Ngô Thị Ngọc Mai | none
2 | Complete the Architecture Design section | Bạch Ngọc Minh Châu&Nguyễn Gia Phú&Nguyễn Duy Mạnh | none
3 | Update ProductBackLog&SRS Documents&Weekly Report for Week 3 | Đinh Tiến Lâm & Trần Văn Đức | none
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | When creating an account on Github, some of you did not register under gmail @fpt.edu.vn or set up an illegal name. | Completed | problem solved
IV. Next Week Plan
# | Project Work Item | Time | Notes (Task Details, etc.) | Memtor | Recording Link
1 | Javascript | 21h - 22h30 (28/09/2021) | Some concepts and some simple syntax | Trần Văn Đức | Link
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | none
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue