## Cover
PROJECT REPORT
GROUP 1
This is a work status report for the week, and identifies plans and goals for the following weeks.
The report is summarized at the end of each week and will be updated in the future.
Members:
+ Trần Văn Đức (Leader- ductvhe141699);
+ Ngô Thị Ngọc Mai (maintnhe151402);
+ Nguyễn Duy Mạnh (MANHNDHE141170);
+ Bạch Ngọc Minh Châu(CHAUBNMHE153019);
+ Nguyễn Gia Phú (PHUNGHE150108);
+ Đinh Tiến Lâm(lamdthe153097).

## Week 4
Time: | 20/09/2021 - 24/09/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Organize file structure on personal computer | Completed | none
2 | Start programming for the project by dividing the work for each member according to the assigned screen. | In Progress | none
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Navbar + Footer + Error (Screen) + Product List | Bạch Ngọc Minh Châu | In Progress
2 | Home Page & Reset Password | Trần Văn Đức | In Progress
3 | Product Details | Nguyễn Duy Mạnh | In Progress
4 | User Login + User Register | Nguyễn Gia Phú | In Progress
5 | User Profile + Change Password | Đinh Tiến Lâm | In Progress
6 | Blog List + Blog Detais | Ngô Thị Ngọc Mai | In Progress
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | none
IV. Next Week Plan
# | Project Work Item | Time | Notes (Task Details, etc.)
1 | none
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | none
VI. Tranning
# | Project Work Item | Time | Notes (Task Details, etc.) | Memtor | Recording Link
1 | Javascript | 21h - 22h30 (28/09/2021) | Some concepts and some simple syntax | Trần Văn Đức | Link
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C19: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue