## Cover
PROJECT REPORT
GROUP 1
This is a work status report for the week, and identifies plans and goals for the following weeks.
The report is summarized at the end of each week and will be updated in the future.
Members:
+ Trần Văn Đức (Leader- ductvhe141699);
+ Ngô Thị Ngọc Mai (maintnhe151402);
+ Nguyễn Duy Mạnh (MANHNDHE141170);
+ Bạch Ngọc Minh Châu(CHAUBNMHE153019);
+ Nguyễn Gia Phú (PHUNGHE150108);
+ Đinh Tiến Lâm(lamdthe153097).

## Week 8
Time: | 20/09/2021 - 24/09/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Continue implementing Iteration 1 | In Progress | none
2 | Continue implementing Iteration 2 | In Progress | none
3 | Start implementating Iteration 3 | In Progress | none
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Notification | Bạch Ngọc Minh Châu | In Progress
2 | Orders List [Sale] | Trần Văn Đức | In Progress
3 | Order Details [Sale] | Nguyễn Duy Mạnh | In Progress
4 | Blog Management | Ngô Thị Ngọc Mai | In Progress
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | none
IV. Next Week Plan
# | Project Work Item | Time | Notes (Task Details, etc.)
1 | Complete three Iteration and Testing project
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | none
VI. Tranning
# | Project Work Item | Time | Notes (Task Details, etc.) | Memtor | Recording Link
1 | none
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C18: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue