## Cover
PROJECT REPORT
GROUP 1
This is a work status report for the week, and identifies plans and goals for the following weeks.
The report is summarized at the end of each week and will be updated in the future.
Members:
+ Trần Văn Đức (Leader- ductvhe141699);
+ Ngô Thị Ngọc Mai (maintnhe151402);
+ Nguyễn Duy Mạnh (MANHNDHE141170);
+ Bạch Ngọc Minh Châu(CHAUBNMHE153019);
+ Nguyễn Gia Phú (PHUNGHE150108);
+ Đinh Tiến Lâm(lamdthe153097).

## Week 2
Time: | 13/09/2021 - 17/09/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS Document | Completed | The specification document is complete, and the documentation is subject to change during the design and implementation of the software system development.
2 | Screen Layout | Completed | The layout is sketchy and references from other websites. More information can be found in the attached specification document
3 | Database | In Progress | Completed diagram, but no data to use yet
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Database Diagram | Ngô Thị Ngọc Mai | Completed
2 | screen layout design | Đinh Tiến Lâm | Screen: Home Page & Product Details & Cart Details & User Login & User Register & Users List [Admin]
3 | screen layout design | Bạch Ngọc Minh Châu | Screen: Cart Completion & Reset Password & Change Password & User Profile
4 | screen layout design | Nguyễn Gia Phú | Screen: My Orders & Order Information & Products List [Sale] & Orders List [Admin]
5 | screen layout design | Ngô Thị Ngọc Mai | Screen: Order Details [Sale] & Feedback & Blogs List & Blog Details
6 | screen layout design | Nguyễn Duy Mạnh + Trần Văn Đức | Screen: Notification & Error
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | None
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Temporarily only plan to start coding next week
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | None
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C20: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue