## BackLog
THE APPLICATION DEVELOPMENT PROJECT TOPIC (SWP391)
ASSIGNMENT FUNCTION DETAILS - ONLINE SHOPPING SYSTEM
Project: Online Shop
# | Function/Screen | Level* | Function/Screen Details | Iteration | Deadline | In Charge | Status | NOTE
1 | Home Page | Simple | It allow everyone can view and search product in website | Iteration 1 | 2021-10-07 | Trần Văn Đức | Not Start
2 | Product List | Simple | Customer can see products that they have just searched | Iteration 1 | 2021-10-07 | Bạch Ngọc Minh Châu | Not Start
2 | Product Details | Medium | Details like description, color, size, ... for customer to choose | Iteration 1 | 2021-10-07 | Nguyễn Duy Mạnh | Not Start
3 | Cart Details | Complex | List of all the products that have been added into the cart | Iteration 2 | 2021-10-17 | Bạch Ngọc Minh Châu | Not Start
4 | User Login | Simple | User will login with account | Iteration 1 | 2021-10-07 | Nguyễn Gia Phú | Not Start
5 | User Register | Simple | Customer can register a new account here | Iteration 1 | 2021-10-07 | Nguyễn Gia Phú | Not Start
6 | User List | Medium | Admin manage accounts | Iteration 2 | 2021-10-17 | Đinh Tiến Lâm | Not Start
7 | Customers List[Seller] | Medium | Show list of all customer | Iteration 2 |  | Nguyễn Duy Mạnh | Not Start
8 | Cart Completion (Place Order) | Medium | Customer can comfirm order information like shipping information,... or change it | Iteration 2 | 2021-10-17 | Bạch Ngọc Minh Châu | Not Start
9 | Reset Password | Simple | User can retrieve password when forgotten by confirming information via email | Iteration 1 | 2021-10-07 | Trần Văn Đức | Not Start
10 | Change Password | Simple | It allow user can change new password | Iteration 1 | 2021-10-07 | Đinh Tiến Lâm | Not Start
11 | User Profile | Medium | User can view and update user's infomation | Iteration 1 | 2021-10-07 | Đinh Tiến Lâm | Not Start
12 | My Orders (xem lịch sử order) (Tổng quát) | Medium | Customers can view history of orders | Iteration 2 | 2021-10-17 | Đinh Tiến Lâm | Not Start
13 | Order Information | Medium | Buyer views the detail of 1 of his orders | literation 1 |  | Nguyễn Duy Mạnh | Not Start
14 | Products List [Sale] | Medium | seller views and manages all products | literation 4 |  | Nguyễn Gia Phú | Not Start
15 | Orders List [Sale] | Medium | Admin views list of all of orders | literation 4 |  | Trần Văn Đức | Not Start
16 | Order Details [Sale] | Medium | The seller can see the orders, they can approve the order or not | literation 4 |  | Nguyễn Duy Mạnh | Not Start
17 | Feedback | Medium | User can view feedback from other customer about a product | literation 4 |  | Ngô Thị Ngọc Mai | Not Start
18 | Blogs List | Medium | List of all the blogs for visitor to read | literation 1 | 2021-10-07 | Ngô Thị Ngọc Mai | Not Start
19 | Blog Details | Medium | Content of a blog | literation 1 | 2021-10-07 | Ngô Thị Ngọc Mai | Not Start
21 | Blog Management |  |  |  |  | Ngô Thị Ngọc Mai
20 | Notification | Medium | Show news about your order, replies,... | literation 5 |  | Bạch Ngọc Minh Châu | Not Start
21 | Sale Dashboard | Complex | Seller views Statistic of the sale of his products | literation 2 | 2021-10-17 | Nguyễn Gia Phú + Trần Văn Đức | Not Start
22 | Error | Simple | Placeholder when error occur | literation 1 | 2021-10-07 | Bạch Ngọc Minh Châu | Completed