## Cover
PROJECT REPORT
GROUP 1
This is a work status report for the week, and identifies plans and goals for the following weeks.
The report is summarized at the end of each week and will be updated in the future.
Members:
+ Trần Văn Đức (Leader- ductvhe141699);
+ Ngô Thị Ngọc Mai (maintnhe151402);
+ Nguyễn Duy Mạnh (MANHNDHE141170);
+ Bạch Ngọc Minh Châu(CHAUBNMHE153019);
+ Nguyễn Gia Phú (PHUNGHE150108);
+ Đinh Tiến Lâm(lamdthe153097).

## Week 1
Time: | 06/09/2021 - 10/09/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS Document | In Progress | There are still some requirements that have not been detailed, resulting in the design of the web framework not being completed such as the estimation of the number of screens, how to design the interface.. Details can be found in the attached word file
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Choose topic of project | All | Online Clothing Shop System
2 | Design database | Ngô Thị Ngọc Mai Nguyễn Gia Phú Nguyễn Duy Mạnh | Only list products, and some information for each product such as product code, type, price and quantity
3 | Find out user and function requirements | Bạch Ngọc Minh Châu Trần Văn Đức | Completed
4 | Analysis and make the SRS document and statistics of the work done and then sum it up in Excel file | Đinh Tiến Lâm | In Progress
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | None
IV. Next Week Plan
# | Project Work Item | Time | Notes (Task Details, etc.) | Link Google Meet | Memtor | Recording Link
1 | Skills Training | 14h30 - 16h (15/09/2021) | FrontEnd_Boostrap 5.0.2 | link | Bạch Ngọc Minh Châu | Link
2 | Continue update SRS documents | 13/09/2021-17/09/2021 | Complete requirements and database | link | All member
3 | Skills Trainning | 21h-22h30(16/09/2021) | JSP + servlet | Link | Trần Văn Đức
4 | Github | 21h-22h30(17/09/2021) | Systax | Link | Đinh Tiến Lâm | link
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | None
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C16: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 2
Time: | 13/09/2021 - 17/09/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS Document | Completed | The specification document is complete, and the documentation is subject to change during the design and implementation of the software system development.
2 | Screen Layout | Completed | The layout is sketchy and references from other websites. More information can be found in the attached specification document
3 | Database | In Progress | Completed diagram, but no data to use yet
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Database Diagram | Ngô Thị Ngọc Mai | Completed
2 | screen layout design | Đinh Tiến Lâm | Screen: Home Page & Product Details & Cart Details & User Login & User Register & Users List [Admin]
3 | screen layout design | Bạch Ngọc Minh Châu | Screen: Cart Completion & Reset Password & Change Password & User Profile
4 | screen layout design | Nguyễn Gia Phú | Screen: My Orders & Order Information & Products List [Sale] & Orders List [Admin]
5 | screen layout design | Ngô Thị Ngọc Mai | Screen: Order Details [Sale] & Feedback & Blogs List & Blog Details
6 | screen layout design | Nguyễn Duy Mạnh + Trần Văn Đức | Screen: Notification & Error
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | None
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Temporarily only plan to start coding next week
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | None
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C20: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 3
Time: | 20/09/2021 - 24/09/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Pending
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
KienNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 4
Time: | 27/09/2021 - 01/10/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Pending
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
KienNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 5
Time: | 04/10/2021 - 08/10/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Pending
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
KienNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 6
Time: | 11/10/2021 - 15/10/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Pending
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
KienNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 7
Time: | 18/10/2021 - 22/10/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Pending
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
KienNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
18/
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 8
Time: | 25/10/2021 - 29/10/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Pending
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
KienNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 9
Time: | 01/11/2021 - 05/11/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Pending
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
KienNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C3: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue