## Wx
PROJECT REPORT
Group | Group 1
Week | <06/09/2021-10/09/2021>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS Documents | In Progress | Just an overview of the product and the languages and technologies that will be used in the project. The requirements have not yet been clarified.
2 | Web skeleton | In Progress | The number of screens to be calculated has been calculated, but the interface has not been designed yet
3 | Design Database | In Progress | Database contains only data for Clothing shop
4 | Create repository on github | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Choose topic of project | All | Online Clothing Shop System
2 | Analysis and make the SRS document | All | Not complete yet
3 | Design database | Ngô Thị Ngọc Mai | The database is in its primitive form, containing only data.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Training Frontend |  | HTML, CSS ,JS
2 | Training Backend |  | Java, Serlvet
3 | Training Database |  | SQL
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes