## BackLog
THE APPLICATION DEVELOPMENT PROJECT TOPIC (SWP391)
ASSIGNMENT FUNCTION DETAILS - ONLINE SHOPPING SYSTEM
Project: Online Shop
# | Function/Screen | Feature | Level* | Function/Screen Details | Iteration | Deadline | In Charge | Status
1 | Home Page | Public | Simple | It allow everyone can view and search product in website | Iteration 1 |  |  | Not Start
2 | Product Details | Public | Medium | Details like description, color, size, ... for customer to choose | Iteration 1 |  |  | Not Start
3 | Cart Details | Customer | Complex | List of all the products that have been added into the cart | Iteration 1 |  |  | Not Start
4 | User Login | Common | Simple | User will login with account | Iteration 1 |  |  | Not Start
5 | User Register | Common | Simple | Customer can register a new account here | Iteration 1 |  |  | Not Start
7 | User Details | Admin | Medium | User can view information about account and update information | Iteration 1 |  |  | Not Start
8 | Reset Password | User | Simple | User can retrieve password when forgotten by confirming information via email | Iteration 1 |  |  | Not Start
9 | Change Password | User | Simple | It allow user can change new password | literation 2 |  |  | Not Start
10 | User List | Admin | Medium | Admin manage accounts | literation 2 |  |  | Not Start
11 | Cart Completion (Place Order) | Customer | Medium | Customer can comfirm order information like shipping information,... or change it | literation 2 |  |  | Not Start
12 | User Profile | User | Medium | User can view and update user's infomation | literation 2 |  |  | Not Start
13 | My Orders (xem lịch sử order) (Tổng quát) | Customer | Medium | Customers can view history of orders | literation 2 |  |  | Not Start
14 | Order Details (chi tiết) | Customer | Medium | Seller views the detail of 1 of his orders | literation 2 |  |  | Not Start
15 | Products List | Marketing | Medium | seller views and manages all products | literation 2 |  |  | Not Start
16 | Product Details | Marketing | Medium | Show information of product | literation 2 |  |  | Not Start
17 | Customers List | Marketing | Medium | Show list of all customer | literation 2 |  |  | Not Start
18 | Customer Details | Marketing | Medium | Show information of customer | literation 2 |  |  | Not Start
19 | Sale Dashboard | Marketing | Complex | Seller views Statistic of the sale of his products | literation 2 |  |  | Not Start
20 | Orders List For All Customer | Sales | Medium | Seller views list of all of orders | literation 2 |  |  | Not Start
21 | Order Details For Seller | Sales | Medium | The seller can see the orders, they can approve the order or not | literation 2 |  |  | Not Start
22 | Feedback | Public | Medium | User can view feedback from other customer about a product | literation 2 |  |  | Not Start
23 | Blogs List | Public | Medium | List of all the blogs for visitor to read | literation 3 |  |  | Not Start
24 | Blog Details | Public | Medium | Content of a blog | literation 3 |  |  | Not Start
25 | Notification | User | Medium | Show news about your order, replies,... | literation 3 |  |  | Not Start
26 | Error | Common | Simple | Placeholder when error occur | literation 3 |  |  | Not Start