## BackLog
THE APPLICATION DEVELOPMENT PROJECT TOPIC (SWP391)
ASSIGNMENT FUNCTION DETAILS - ONLINE SHOPPING SYSTEM
Project: Online Shop
# | Function/Screen | Level* | Function/Screen Details | Iteration | Deadline | In Charge | Status | NOTE
1 | Home Page | Simple | It allow everyone can view and search product in website | Iteration 1 | 2021-10-07 | Trần Văn Đức | Starting
2 | Product List | Simple | Customer can see products that they have just searched | Iteration 1 | 2021-10-07 | Bạch Ngọc Minh Châu | Starting
3 | Product Details | Medium | Details like description, color, size, ... for customer to choose | Iteration 1 | 2021-10-07 | Nguyễn Duy Mạnh | Starting
4 | Cart Details | Complex | List of all the products that have been added into the cart | Iteration 2 | 2021-10-17 | Bạch Ngọc Minh Châu | Starting
5 | User Login | Simple | User will login with account | Iteration 1 | 2021-10-07 | Nguyễn Gia Phú | Starting
6 | User Register | Simple | Customer can register a new account here | Iteration 1 | 2021-10-07 | Nguyễn Gia Phú | Starting
7 | User List | Medium | Admin manage accounts | Iteration 2 | 2021-10-17 | Đinh Tiến Lâm | Starting
8 | Customers List[Seller] | Medium | Show list of all customer | Iteration 2 | 2021-10-17 | Nguyễn Duy Mạnh | Starting
9 | Cart Completion (Place Order) | Medium | Customer can comfirm order information like shipping information,... or change it | Iteration 2 | 2021-10-17 | Bạch Ngọc Minh Châu | Starting
10 | Reset Password | Simple | User can retrieve password when forgotten by confirming information via email | Iteration 1 | 2021-10-07 | Trần Văn Đức | Starting
11 | Change Password | Simple | It allow user can change new password | Iteration 1 | 2021-10-07 | Đinh Tiến Lâm | Starting
12 | User Profile | Medium | User can view and update user's infomation | Iteration 1 | 2021-10-07 | Đinh Tiến Lâm | Starting
13 | My Orders (xem lịch sử order) (Tổng quát) | Medium | Customers can view history of orders | Iteration 2 | 2021-10-17 | Đinh Tiến Lâm | Starting
14 | Order Information | Medium | Buyer views the detail of 1 of his orders | Iteration 2 | 2021-10-17 | Nguyễn Duy Mạnh | Starting
15 | Products List [Sale] | Medium | seller views and manages all products | literation 2 | 2021-10-17 | Nguyễn Gia Phú | Starting
16 | Orders List [Sale] | Medium | Admin views list of all of orders | literation 3 | 2021-11-06 | Trần Văn Đức | Starting
17 | Order Details [Sale] | Medium | The seller can see the orders, they can approve the order or not | literation 3 | 2021-11-06 | Nguyễn Duy Mạnh | Starting
18 | Feedback | Medium | User can view feedback from other customer about a product | literation 2 | 2021-10-17 | Ngô Thị Ngọc Mai | Starting
19 | Blogs List | Medium | List of all the blogs for visitor to read | literation 1 | 2021-10-07 | Ngô Thị Ngọc Mai | Starting
20 | Blog Details | Medium | Content of a blog | literation 1 | 2021-10-07 | Ngô Thị Ngọc Mai | Starting
21 | Blog Management | Medium | CRUD for Blog | literation 3 | 2021-11-06 | Ngô Thị Ngọc Mai | Starting
22 | Notification | Medium | Show news about your order, replies,... | literation 3 | 2021-11-06 | Bạch Ngọc Minh Châu | Starting
23 | Sale Dashboard | Complex | Seller views Statistic of the sale of his products | literation 2 | 2021-10-17 | Nguyễn Gia Phú + Trần Văn Đức | Starting
24 | Error | Simple | Placeholder when error occur | literation 1 | 2021-10-07 | Bạch Ngọc Minh Châu | Completed